UNIVERSIDAD DE LAS FUERZAS ARMADAS ESPE

Department of Computer Science – Software Engineering

ADVANCED WEB DEVELOPMENT

Names: Esteban Quiroga, Angel Sabando, David Rodriguez

NRC: 30716

Date: 2/5/2025

Accounting System – Features Document

Product Backlog Decomposition into Features by Module

Features Summary

| ID | Feature | Module | Sprints | Responsible | Total Hrs |
| --- | --- | --- | --- | --- | --- |
| FT-01 | Access & User Management | Module 1 | Sprint 1 (2 weeks) | E.Q / A.S / D.R | 14 hrs |
| FT-02 | Integration with SRI Online Portal | Module 2 | Sprint 2 (1 week) | E.Q / A.S / D.R | 14 hrs |
| FT-03 | Invoice Download & Management from SRI | Module 3 | Sprint 4 (1 week) | E.Q / A.S / D.R | 14 hrs |
| FT-04 | ATS Generation & Validation in XLSM | Module 4 | Sprint 7 (1 week) | E.Q / A.S / D.R | 19 hrs |
| FT-05 | ATS Export to XML Format (DIMM SRI) | Module 6 | Sprint 10 (2 weeks) | E.Q / A.S / D.R | 14 hrs |
| FT-06 | ATS Process Flow Traceability & Control | Module 7 | Sprint 12 (1 week) | E.Q / A.S / D.R | 14 hrs |

Feature Details

FT-01 – Access & User Management

| FT-01 – Access & User Management |  |
| --- | --- |
| Description | Allows taxpayers to register with their RUC and log in securely to access all modules of the accounting system. |
| Objective | Ensure each user is uniquely identified by their RUC, controlling access in a secure manner. |
| Module | Module 1 – Registration and Authentication |
| Sprints | Sprint 1 (2 weeks) |
| Associated RFs | RF-01, RF-02 |
| Responsible | Esteban Quiroga (T-01-03) ¦ Angel Sabando (T-01-02, T-01-04) ¦ David Rodriguez (T-01-01) |
| Business Rules | BR-02 (Taxpayer uniqueness) |

Associated User Stories

| ID | User Story | Actor | Priority | Status |
| --- | --- | --- | --- | --- |
| US-01 | As a taxpayer I need to create an account linked to my RUC with my personal data. | Taxpayer | High | Prioritized |
| US-02 | As a user I need to log in with my credentials to access my modules. | User | High | Prioritized |

Technical Tasks

| Task ID | Task | Rel. with | Responsible | Sprint | Hrs |
| --- | --- | --- | --- | --- | --- |
| T-01-01 | Create user registration form with respective validations. | US-01 | David Rodriguez | Sprint 1 | 4 |
| T-01-02 | Model database to store users. | DBA | Angel Sabando | Sprint 1 | 4 |
| T-01-03 | Program login form with respective validations. | DBA | Esteban Quiroga | Sprint 1 | 3 |
| T-01-04 | Connect database with registration form. | DBA | Angel Sabando | Sprint 1 | 3 |

Applicable Non-Functional Requirements

| NFR ID | Description |
| --- | --- |
| NFR-02 | Intuitive interface with clear navigation between modules. |
| NFR-04 | Encrypted HTTPS/TLS 1.2+ communication across all modules. |
| NFR-07 | Compatible with Chrome, Firefox, and Edge (last 2 versions). |

FT-02 – Integration with SRI Online Portal

| FT-02 – Integration with SRI Online Portal |  |
| --- | --- |
| Description | Connects the system to the 'SRI en linea' portal using taxpayer credentials, managing authentication, remote errors, and TLS security. |
| Objective | Establish a secure and reliable channel between the platform and the SRI to operate on behalf of the taxpayer. |
| Module | Module 2 – SRI Integration |
| Sprints | Sprint 2 (1 week) + Sprint 3 (1 week) |
| Associated RFs | RF-03 |
| Responsible | Esteban Quiroga (T-02-01) ¦ Angel Sabando (T-02-02) ¦ David Rodriguez (T-02-03) |
| Business Rules | BR-02 (Uniqueness), BR-05 (SRI Updates) |

Associated User Stories

| ID | User Story | Actor | Priority | Status |
| --- | --- | --- | --- | --- |
| US-03 (F1) | As an accountant I need to link to SRI en linea with my credentials (basic authentication). | Accountant | High | Prioritized |
| US-03 (F2) | As an accountant I need the system to handle connection errors and apply TLS security. | Accountant | High | Prioritized |

Technical Tasks

| Task ID | Task | Rel. with | Responsible | Sprint | Hrs |
| --- | --- | --- | --- | --- | --- |
| T-02-01 | Create SRI connection interface using user credentials. | US-03 | Esteban Quiroga | Sprint 2 | 7 |
| T-02-02 | Validate error handling and ensure login data is not leaked. | US-03 | Angel Sabando | Sprint 3 | 5 |
| T-02-03 | Perform connection tests between the system and the SRI website. | US-03 | David Rodriguez | Sprint 3 | 2 |

Applicable Non-Functional Requirements

| NFR ID | Description |
| --- | --- |
| NFR-04 | All communication with SRI must use HTTPS or TLS 1.2+. |
| NFR-05 | The system must be available at least 99% of the time monthly. |
| NFR-08 | The system must fail in less than 0.05% of executions. |

FT-03 – Invoice Download & Management from SRI

| FT-03 – Invoice Download & Management from SRI |  |
| --- | --- |
| Description | Allows downloading invoices from the SRI filtered by tax period (monthly or semi-annual), storing them locally, and loading an XML directory for validation. |
| Objective | Automate invoice retrieval from SRI while respecting tax periods, eliminating manual downloads. |
| Module | Module 3 – Invoice Management |
| Sprints | Sprint 4 (1 week) + Sprint 5 (1 week) + Sprint 6 (2 weeks) |
| Associated RFs | RF-04, RF-05, RF-06 |
| Responsible | Esteban Quiroga (T-03-01) ¦ Angel Sabando (T-03-03) ¦ David Rodriguez (T-03-02, T-03-04) |
| Business Rules | BR-01 (Tax periods), BR-02 (Uniqueness) |

Associated User Stories

| ID | User Story | Actor | Priority | Status |
| --- | --- | --- | --- | --- |
| US-04 (F1) | As an accountant I need to download invoices from the SRI (basic download). | Accountant | High | Prioritized |
| US-04 (F2) | As an accountant I need to filter invoices by month or semester (BR-01). | Accountant | High | Prioritized |
| US-05 | As an accountant I need to load an XML invoice directory so the system can validate them. | Accountant | High | Prioritized |

Technical Tasks

| Task ID | Task | Rel. with | Responsible | Sprint | Hrs |
| --- | --- | --- | --- | --- | --- |
| T-03-01 | Create invoice download module linked to the user account. | US-04 | Esteban Quiroga | Sprint 4 | 4 |
| T-03-02 | Develop a tax period filter system. | US-04 | David Rodriguez | Sprint 5 | 4 |
| T-03-03 | Create a compatible directory for managing downloaded invoices. | US-04 | Angel Sabando | Sprint 5 | 3 |
| T-03-04 | Create invoice directory upload and validation interface. | US-05 | David Rodriguez | Sprint 6 | 3 |

Applicable Non-Functional Requirements

| NFR ID | Description |
| --- | --- |
| NFR-01 | Support processing of more than 5,000 invoices per month. |
| NFR-03 | Generate the ATS in a maximum of 5 seconds with up to 1,000 invoices. |
| NFR-06 | Format updates without affecting other modules. |

FT-04 – ATS Generation & Validation in XLSM

| FT-04 – ATS Generation & Validation in XLSM |  |
| --- | --- |
| Description | Automatically generates the ATS in XLSM according to the SRI schema, validates each field, and produces an error log for correction before exporting to XML. |
| Objective | Reduce typing errors and ensure the ATS complies with the SRI technical specification before being exported. |
| Module | Module 4 – XLSM Generation / Module 5 – XLSM Validation |
| Sprints | Sprint 7 (1 week) + Sprint 8 (2 weeks) + Sprint 9 (2 weeks) |
| Associated RFs | RF-07, RF-08 |
| Responsible | Esteban Quiroga (T-04-01, T-05-01) ¦ Angel Sabando (T-04-02, T-05-02) ¦ David Rodriguez (T-04-03) |
| Business Rules | BR-02 (Uniqueness), BR-03 (ATS format and validation) |

Associated User Stories

| ID | User Story | Actor | Priority | Status |
| --- | --- | --- | --- | --- |
| US-06 (F1) | As an accountant I need to generate the ATS in XLSM from the loaded invoices. | Accountant | High | Prioritized |
| US-07 | As an accountant I need to edit and validate the XLSM to detect errors before the final XML. | Accountant | High | Prioritized |

Technical Tasks

| Task ID | Task | Rel. with | Responsible | Sprint | Hrs |
| --- | --- | --- | --- | --- | --- |
| T-04-01 | Transfer invoices to ATS XLSM format validating data transcription. | US-06 | Esteban Quiroga | Sprint 7 | 5 |
| T-04-02 | Validate each ATS field according to invoice XML tags. | US-06 | Angel Sabando | Sprint 8 | 5 |
| T-04-03 | Enable download of the generated ATS file in XLSM. | US-06 | David Rodriguez | Sprint 8 | 2 |
| T-05-01 | Develop full validation of the XLSM file. | US-07 | Esteban Quiroga | Sprint 9 | 5 |
| T-05-02 | Design error log system and enable XML creation. | US-07 | Angel Sabando | Sprint 9 | 2 |

Applicable Non-Functional Requirements

| NFR ID | Description |
| --- | --- |
| NFR-03 | ATS generation in a maximum of 5 seconds (up to 1,000 invoices). |
| NFR-06 | ATS format updates without affecting other modules. |
| NFR-08 | Failure rate below 0.05% in ATS generation. |

FT-05 – ATS Export to XML Format (DIMM SRI)

| FT-05 – ATS Export to XML Format (DIMM SRI) |  |
| --- | --- |
| Description | Converts the validated XLSM file to the XML format required by the SRI DIMM in UTF-8 encoding and makes it available for download and official submission. |
| Objective | Generate the final XML file complying with the SRI DIMM schema, ready for official submission. |
| Module | Module 6 – XML Export |
| Sprints | Sprint 10 (2 weeks) + Sprint 11 (2 weeks) |
| Associated RFs | RF-09 |
| Responsible | Esteban Quiroga (T-06-01) ¦ Angel Sabando (T-06-02) ¦ David Rodriguez (T-06-03) |
| Business Rules | BR-04 (XML format required by SRI), BR-05 (SRI Updates) |

Associated User Stories

| ID | User Story | Actor | Priority | Status |
| --- | --- | --- | --- | --- |
| US-08 (F1) | As an accountant I need to generate the ATS in XML UTF-8 from the validated XLSM. | Accountant | High | Prioritized |
| US-08 (F2) | As an accountant I need the XML to be compatible with the SRI DIMM schema. | Accountant | High | Prioritized |

Technical Tasks

| Task ID | Task | Rel. with | Responsible | Sprint | Hrs |
| --- | --- | --- | --- | --- | --- |
| T-06-01 | Develop XML creation from the validated XLSM. | US-08 | Esteban Quiroga | Sprint 10 | 5 |
| T-06-02 | Validate that the XML complies with the SRI DIMM schema. | US-08 | Angel Sabando | Sprint 11 | 5 |
| T-06-03 | Implement XML download with applied validations. | US-08 | David Rodriguez | Sprint 11 | 4 |

Applicable Non-Functional Requirements

| NFR ID | Description |
| --- | --- |
| NFR-01 | Support large volume exports without degrading performance. |
| NFR-04 | Encrypted HTTPS/TLS communication during the export process. |
| NFR-08 | Failure rate below 0.05% in XML generation. |

FT-06 – ATS Process Flow Traceability & Control

| FT-06 – ATS Process Flow Traceability & Control |  |
| --- | --- |
| Description | Provides a control panel showing the status of each step in the ATS process: from SRI linking to XML export, with date and action records. |
| Objective | Ensure full visibility and audit of the workflow, facilitating detection of incomplete steps. |
| Module | Module 7 – Flow Control / Traceability |
| Sprints | Sprint 12 (1 week) |
| Associated RFs | RF-05 (ATS Manager Module) |
| Responsible | Esteban Quiroga (T-07-01) ¦ Angel Sabando (T-07-02) |
| Business Rules | BR-03 (Format and validation), BR-05 (SRI Updates) |

Associated User Stories

| ID | User Story | Actor | Priority | Status |
| --- | --- | --- | --- | --- |
| US-09 | As an auditor I need to view the complete history of the ATS generation process. | Auditor/Admin | Medium | Prioritized |

Technical Tasks

| Task ID | Task | Rel. with | Responsible | Sprint | Hrs |
| --- | --- | --- | --- | --- | --- |
| T-07-01 | Create widget with ATS process steps and their status (completed / pending / blocked). | US-09 | Esteban Quiroga | Sprint 12 | 7 |
| T-07-02 | Connect widget to each module for automatic update upon task completion. | US-09 | Angel Sabando | Sprint 12 | 7 |

Applicable Non-Functional Requirements

| NFR ID | Description |
| --- | --- |
| NFR-02 | Intuitive interface with clear navigation and minimal task execution times. |
| NFR-05 | 99% monthly availability to ensure continuous access to the history. |
| NFR-07 | Compatible with Chrome, Firefox, and Edge (last 2 versions). |

Effort Distribution by Team Member

| Team Member | Assigned Tasks | Estimated Total |
| --- | --- | --- |
| Esteban Quiroga | T-01-03, T-02-01, T-03-01, T-04-01, T-05-01, T-06-01, T-07-01 | 36 hrs |
| Angel Sabando | T-01-02, T-01-04, T-02-02, T-03-03, T-04-02, T-05-02, T-06-02, T-07-02 | 34 hrs |
| David Rodriguez | T-01-01, T-02-03, T-03-02, T-03-04, T-04-03, T-06-03 | 30 hrs |
| PROJECT TOTAL | 21 tasks distributed across 12 sprints | 100 hrs |

Practical Case – ATS Accounting System  |  ESPE 2025